## Sheet1
Enter Your Name |  |  | First and last name
Enter your Mentor's Name |  |  | First and last name
Enter your Capstone Chair Name |  |  | First and last name
Enter the Capstone Start Date | 2025-01-01 |  | the date that you intend to start learning the methods and collecting data
Enter Planned Presentation Date | 2025-12-11 |  | Estimate the day you will present your findings - doesn't need to be exact
Number of days | 344 |  | Number of days between capstone start and your presentation
completion date
Assignment Milestones | Suggested | Actual | Comments
Prepare
• Capstone Authorization Packet | 2024-12-31 |  | Must be completed before Starting the Capstone Project
• Capstone Start Date | 2025-01-01 | 2025-01-01 | To learn the methods and collect preliminary data
Propose
• Outline Capstone Proposal | 2025-04-24 12:29 |  | Formulate a hypothesis and specific aims.
• Submit Capstone Proposal | 2025-08-02 06:43 |  | Should be scheduled before final semester
• Complete Data Collection | 2025-08-16 06:43 |  | Ideally completed before final semester
Present
• Practice Presentation | as needed |  | Plan at least 2 practice sessions
• Complete Data Analysis | 2025-09-15 06:43 |  | Ideally before you submit your written draft
• Draft Written Report | 2025-11-27 |  | submit a draft to your committee two weeks before you present
• Present Capstone | 2025-12-11 | 2025-12-11
• Submit Written Report | end of semester |  | At least a week before the end of the semester to give your committee enough time to review
• Submit Digital Resources | end of semester |  | At the end of your final semester when all is complete
Formulas:
Suggested = [Suggested, row above]+14
Suggested = [Suggested, row below]-14
Actual = [Suggested]
Instructions: Fill in the Yellow Input Boxes to set the range of dates from the Start of the Capstone to the Estimated Capstone Presentation day. This will set the suggested dates for the milestone assignments in the Assignment Milestones table below. Then, in the table, fill the white boxes with the actual deadlines that you will use for your Capstone Timeline.

## Sheet2
Start Date | 2025-06-01
| 2025-09-15 | 106 | 0.32817
Capstone Proposal | 2025-12-20 | 202 | 0.62539
Presentation Day | 2026-04-20 | 323
Start Date | 2025-01-01
Presentation Day | 2025-12-11 | 344
Capstone Proposal | 2025-08-04 03:12